FinCopilot

Conversational Finance Copilot for Students

Hackathon Project Plan — 36 Hours to Build, 5 Minutes to Present

# 1. Team & Role Assignments

Three developers, clearly divided responsibilities to avoid merge conflicts and maximize parallel work.

| Role | Person | Owns |
| --- | --- | --- |
| Backend 1 (BE1) | Developer A | API server, database schema, financial model engine, scenario simulation logic |
| Backend 2 (BE2) | Developer B | AI integration (LLM prompts, structured extraction), critical issue detection rules, what-if endpoint |
| Frontend (FE) | Developer C | Chat UI, financial profile display, scenario results visualization, demo polish |

# 2. Recommended Tech Stack

Keep it simple. Use tools your team already knows. Below is a sensible default; swap anything you are more comfortable with.

| Layer | Tool | Why |
| --- | --- | --- |
| Frontend | Next.js or React + Vite | Fast setup, easy deploy |
| Backend | Python (FastAPI) or Node (Express) | Quick endpoints, good LLM libs |
| Database | SQLite or Supabase (Postgres) | Zero config or hosted free tier |
| AI / LLM | Claude API (Sonnet) | Strong at conversation + extraction |
| Deploy | Vercel (FE) + Railway (BE) | Free tier, fast deploys |

# 3. Build Phases — Sequential Order

The 36 hours are split into 5 phases. Each phase has a clear goal, and work is parallelized across the team. Finish each phase before moving on; do not skip ahead.

## Phase 0: Setup & Scaffold (Hours 0–2)

Goal: Everyone can run the app locally and push code. No feature work yet.

| Time | Task | Owner |
| --- | --- | --- |
| 0–0.5h | Create GitHub repo, set up branching strategy (main + feature branches) | BE1 |
| 0–0.5h | Scaffold frontend project (Next.js/Vite), install UI library (shadcn or Tailwind) | FE |
| 0.5–1h | Scaffold backend project, set up FastAPI/Express with a /health endpoint | BE1 |
| 0.5–1h | Set up LLM API key, test a basic prompt call, confirm it works end-to-end | BE2 |
| 1–2h | Define and agree on the API contract (endpoints, request/response shapes) | ALL |
| 1–2h | Set up database schema (users, profiles, conversations) | BE1 |

Checkpoint: Frontend can call backend /health. Backend can call LLM. Database tables exist. Everyone has cloned and can run locally.

## Phase 1: Conversational Onboarding (Hours 2–10)

Goal: A user can chat with the app, answer financial questions, and the app stores a structured financial profile. This is the foundation for everything else.

| Time | Task | Owner |
| --- | --- | --- |
| 2–4h | Build the chat API endpoint: accepts user message, returns AI response | BE2 |
| 2–4h | Write the onboarding system prompt: guide the LLM to ask about income, expenses, debt, accounts, and goals one topic at a time | BE2 |
| 2–5h | Build the financial profile data model and CRUD endpoints (create/read/update profile) | BE1 |
| 4–7h | Build structured extraction: after each AI response, extract financial data from the conversation into the profile schema using a second LLM call with JSON mode | BE2 |
| 2–6h | Build the chat interface: message list, input box, send button, loading states | FE |
| 6–10h | Build the live financial profile sidebar: shows income, expenses, debt, accounts, and goal updating in real-time as the user chats | FE |
| 7–10h | Integration testing: chat end-to-end, confirm profile populates correctly | ALL |

Checkpoint: User can have a natural conversation. Their financial profile builds up live on screen. Data persists in the database.

## Phase 2: Critical Issue Detection (Hours 10–18)

Goal: The app analyzes the user’s profile and flags financial issues with explanations. This is rule-based, not AI-generated.

| Time | Task | Owner |
| --- | --- | --- |
| 10–14h | Build the rules engine: write deterministic rules that check the profile for issues | BE1 |
|  | Rule 1: High-interest debt + idle savings = suggest reallocation Rule 2: Savings in non-interest account = suggest HISA Rule 3: Variable income + low emergency buffer = flag risk Rule 4: Monthly expenses > income = unsustainable Rule 5: Goal timeline unrealistic given current savings rate | BE1 |
| 10–14h | Build the explanation layer: for each triggered rule, use the LLM to generate a plain-language explanation of what the issue is, why it matters, and how urgent it is | BE2 |
| 14–18h | Build the issues panel in the UI: show flagged issues as cards with severity indicators (critical / warning / tip), explanation text, and suggested actions | FE |
| 16–18h | Integration: trigger issue detection after onboarding completes, display results | ALL |

Checkpoint: After chatting, the app shows 2–4 personalized financial issues with clear, helpful explanations. Rules are deterministic and testable.

## Phase 3: What-If Scenario Engine (Hours 18–28)

Goal: The user can ask “what if” questions in chat and see simulated outcomes compared to their current trajectory. This is the flagship feature.

| Time | Task | Owner |
| --- | --- | --- |
| 18–22h | Build the simulation engine: takes a profile + a set of changes and projects monthly cash flow, debt paydown, and savings growth over N months | BE1 |
| 18–22h | Build the scenario parser: use the LLM to extract structured scenario parameters from natural language (e.g., “What if I work 5 more hours?” → { income_change: +X }) | BE2 |
| 22–24h | Build the compare endpoint: runs simulation for current state AND modified state, returns both trajectories | BE1 + BE2 |
| 18–24h | Build scenario results UI: side-by-side or overlay comparison charts showing current vs. hypothetical trajectory for cash flow, debt, and savings | FE |
| 24–26h | Build the AI summary: after simulation runs, use LLM to generate a plain-language verdict (“Yes, this is feasible if...” or “This puts you at risk because...”) | BE2 |
| 26–28h | Integration and edge case testing: test multiple scenario types, handle missing data gracefully | ALL |

Checkpoint: User asks “Can I afford to move out?” in chat and sees a visual comparison of outcomes with a clear AI-generated verdict.

## Phase 4: Polish, Demo Prep & Deploy (Hours 28–36)

Goal: Ship a working, deployed app. Prepare a tight 5-minute demo that tells a story.

| Time | Task | Owner |
| --- | --- | --- |
| 28–30h | UI polish: consistent colors, typography, spacing, mobile-friendly layout, loading skeletons | FE |
| 28–30h | Bug fixes, error handling, edge cases (empty profile, API timeouts, malformed input) | BE1 + BE2 |
| 30–32h | Deploy frontend and backend to hosting. Test the live URL end-to-end. | BE1 |
| 30–32h | Seed a demo user profile so you can skip onboarding during the live demo | BE2 |
| 32–34h | Write the demo script (see Section 5 below). Practice it at least 3 times. | ALL |
| 34–36h | Final rehearsal with timer. Prepare backup screenshots in case of live demo failure. | ALL |

Checkpoint: App is live. Demo script is rehearsed. Backup plan is ready. Team is confident.

# 4. Demo Script (5 Minutes)

Structure the demo as a story, not a feature tour. Judges remember stories.

| Time | Beat | What to Show / Say |
| --- | --- | --- |
| 0:00–0:40 | The Problem | “Students have big financial goals but no idea if they’re realistic. Budgeting apps tell you where money went. Nothing helps you decide what to do next.” |
| 0:40–1:30 | The Solution | Introduce FinCopilot. One-line pitch. Show the landing screen briefly. |
| 1:30–2:30 | Live Demo: Chat | Show the pre-seeded conversation. Highlight how the profile builds up live in the sidebar as the student answers questions. |
| 2:30–3:15 | Live Demo: Issues | Show the flagged issues. Read one aloud. Emphasize: “This is rule-based, not hallucinated. We can explain exactly why each issue was flagged.” |
| 3:15–4:15 | Live Demo: What-If | Ask “Can I afford to move out in 6 months?” Show the comparison chart. Read the AI verdict. This is the wow moment. |
| 4:15–5:00 | Architecture + Close | Show one slide: AI for conversation + rules for reasoning. Close with: “We built a tool that gives students the confidence to make real financial decisions.” |

# 5. Key Principles

Keep these in mind throughout the entire build:

| Principle | What It Means in Practice |
| --- | --- |
| AI for language, rules for math | Never let the LLM calculate projections directly. It parses input and explains output. Deterministic code does the financial reasoning. |
| Depth over breadth | One polished scenario flow (e.g., “can I move out?”) beats five half-working ones. Nail the core loop. |
| Always be demo-ready | After every phase, the app should be in a showable state. Never break main. |
| Seed your demo data | Do not rely on live onboarding during the 5-minute demo. Pre-load a compelling student profile. |
| Cut scope ruthlessly | If something is not working by 75% of the phase’s time, simplify or hardcode it. Shipping > perfection. |

# 6. If You’re Running Out of Time

Things you can cut or simplify without hurting the demo:

- User authentication — use a single hardcoded user for the demo

- Database persistence — keep the profile in memory if DB setup takes too long

- Multiple goals — support only one goal in the MVP (this is already in the spec)

- Bank statement upload — this was always a stretch goal, skip it entirely

- Deployment — demo from localhost if hosting fails; judges care about the product, not the infra

- Multiple scenario types — nail one great “can I afford X?” flow rather than supporting every question type

Things you should NOT cut:

- The live profile sidebar (this is visually impressive and easy to demo)

- At least 3 working detection rules (shows the deterministic reasoning angle)

- The comparison chart for what-if scenarios (this is your wow moment)

- The AI-generated verdict on scenarios (ties the whole experience together)